## Primoris Trend Report by Descri
Primoris Trend Report by Description
To-date date - Current date; Job - 55310.M - EARP PV SOLAR PROJECT; Include jobs with no activity - Yes; Beginning Account - ; Ending Account - ; Include accounts with no activity - (All); Percent complete to begin projection - 25 %; Cost variance threshold - 5%; Period ending date - 10/4/2023
Period Dates: 09/11/2023 to 10/04/2023
Projection % Complete: 0.25
Job 55310.M |  |  |  | Job Status
[7 empty] | Current |  | Billings
[5 empty] | Contract† |  | Contract |  | Actual Cost |  | Projections
|  |  |  | Revenue | 0 |  | 0 |  | 0 |  | 0
|  |  |  | Costs | 832528 |  | 832528 |  | 1240900.9144 |  | 1451497.2123
|  |  |  | Profit | -832528 |  | -832528 |  | -1240900.9144 |  | -1451497.2123
Cost Variance by Account |  |  |  | GP%
|  |  | ESTIMATED |  |  | JOB TO DATE |  |  |  | PROJECTED (CALCULATED) |  |  |  | TREND BY WEEK | [15 empty] | JOB TO DATE TRENDS
JOB TRACKING ACCOUNT DETAILED COST PROJECTION | [13 empty] | WE 09.17.23 |  |  |  | WE 09.24.23 |  |  |  | WE 10.01.23 |  |  |  | WE 10.08.23 |  |  |  | WE 10.08.23
Type |  | UM | Units | UC | Cost | Units | UC | Cost | UC Var | Units | UC | Final Cost | Cost Var | Units | UC | Cost | UC Var | Units | UC | Cost | UC Var | Units | UC | Cost | UC Var | Units | UC | Cost | UC Var | % complete on production | % cost usage | UNITS left to complete | COST + -
Account: 0104- 8100- M00 SURVEY PILES
| Labor |  |  | 34532 | 34532 |  | 2496.4539 | 29957.4467 | 32035.5461 |  | 2496.4539 | 29957.4467 | -4574.5533 |  |  | 422.5445 | 34532 |  |  | 249.283 | 34532 |  |  | 1449.4693 | 34532 |  |  | 124.6415 | 34532
Total For Account LS |  | LS | 1 | 34532 | 34532 | 12 | 2496.4539 | 29957.4467 | 32035.5461 | 12 | 2496.4539 | 29957.4467 | -4574.5533 | 0 | 0 | 422.5445 | 34532 | 0 | 0 | 249.283 | 34532 | 0 | 0 | 1449.4693 | 34532 | 0 | 0 | 124.6415 | 34532 | 1200% | 86.75% | -11 | 4574.5533
Account: 0104- 8100- M01 UNLOAD PILES
| Labor |  |  | 103.4286 | 5068 |  | 51.6048 | 2528.636 | 51.8238 |  | 51.6048 | 2528.636 | -2539.364 |  |  | 0 | 103.4286 |  |  | 0 | 103.4286 |  |  | 0 | 103.4286 |  |  | 0 | 103.4286
| Equipment |  |  | 30.3878 | 1489 |  | 13.0204 | 638 | 17.3673 |  | 13.0204 | 638 | -851 |  |  | 0 | 30.3878 |  |  | 0 | 30.3878 |  |  | -418 | 30.3878 |  |  | 0 | 30.3878
Total For Account LOAD |  | LOAD | 49 | 133.8163 | 6557 | 49 | 64.6252 | 3166.636 | 69.1911 | 49 | 64.6252 | 3166.636 | -3390.364 | 0 | 0 | 0 | 133.8163 | 0 | 0 | 0 | 133.8163 | 0 | 0 | -418 | 133.8163 | 0 | 0 | 0 | 133.8163 | 100% | 48.29% | 0 | 3390.364
Account: 0104- 8100- M02 STAGE PILES
| Labor |  |  | 2.5979 | 37239 |  | 3.9385 | 56453.9064 | -1.3405 |  | 3.9385 | 56453.9064 | 19214.9064 |  |  | 0 | 2.5979 |  |  | 0 | 2.5979 |  |  | 1992.8604 | 2.5979 |  |  | 0 | 2.5979
| Equipment |  |  | 0.69241 | 9925 |  | 0.70476 | 10102 | -0.012348 |  | 0.70476 | 10102 | 177 |  |  | 0 | 0.69241 |  |  | 0 | 0.69241 |  |  | -1540 | 0.69241 |  |  | 0 | 0.69241
Total For Account EACH |  | EACH | 14334 | 3.2904 | 47164 | 14334 | 4.6432 | 66555.9064 | -1.3529 | 14334 | 4.6432 | 66555.9064 | 19391.9064 | 0 | 0 | 0 | 3.2904 | 0 | 0 | 0 | 3.2904 | 0 | 0 | 452.8604 | 3.2904 | 0 | 0 | 0 | 3.2904 | 100% | 141.1% | -1.819e-12 | -19391.9064
Account: 0104- 8100- M03 DRIVE NON-TRACKER PILES
| Labor |  |  | 18.8531 | 4619 |  | 15.7439 | 3857.26 | 3.1091 |  | 15.7439 | 3857.26 | -761.74 |  |  | 0 | 18.8531 |  |  | 0 | 18.8531 |  |  | 0 | 18.8531 |  |  | 0 | 18.8531
| Equipment |  |  | 32.5102 | 7965 |  | 22.9224 | 5616 | 9.5878 |  | 22.9224 | 5616 | -2349 |  |  | 1152 | 32.5102 |  |  | 1152 | 32.5102 |  |  | 0 | 32.5102 |  |  | 0 | 32.5102
Total For Account EACH |  | EACH | 245 | 51.3633 | 12584 | 245 | 38.6664 | 9473.26 | 12.6969 | 245 | 38.6664 | 9473.26 | -3110.74 | 0 | 0 | 1152 | 51.3633 | 0 | 0 | 1152 | 51.3633 | 0 | 0 | 0 | 51.3633 | 0 | 0 | 0 | 51.3633 | 100% | 75.28% | 0 | 3110.74
Account: 0104- 8100- M04 DRIVE PILES
| Labor |  |  | 5.7573 | 82525 |  | 6.4255 | 92102.4891 | -0.66817 |  | 6.4255 | 92102.4891 | 9577.4891 |  |  | 2174.3206 | 5.7573 |  | 19.1735 | 2147.4324 | -13.4162 |  | 1.644 | 384.6999 | 4.1133 |  | 0 | 0 | 5.7573
| Equipment |  |  | 5.9674 | 85536 |  | 7.8746 | 112874 | -1.9072 |  | 7.8746 | 112874 | 27338 |  |  | 0 | 5.9674 |  | 0 | 0 | 5.9674 |  | 0 | 0 | 5.9674 |  | 0 | 0 | 5.9674
Total For Account EACH |  | EACH | 14334 | 11.7246 | 168061 | 14334 | 14.3 | 204976.4891 | -2.5754 | 14334 | 14.3 | 204976.4891 | 36915.489 | 0 | 0 | 2174.3206 | 11.7246 | 112 | 19.1735 | 2147.4324 | -7.4489 | 234 | 1.644 | 384.6999 | 10.0806 | 0 | 0 | 0 | 11.7246 | 100% | 122% | 0 | -36915.489
Account: 0104- 8100- M05 PULL TEST FOUNDATION
| Labor |  |  | 601.4167 | 7217 |  |  | 0 | 601.4167 |  | 601.4167 | 7217 | 0 |  |  | 0 | 601.4167 |  |  | 0 | 601.4167 |  |  | 0 | 601.4167 |  |  | 0 | 601.4167
| Equipment |  |  | 467.8333 | 5614 |  |  | 0 | 467.8333 |  | 467.8333 | 5614 | 0 |  |  | 0 | 467.8333 |  |  | 0 | 467.8333 |  |  | 0 | 467.8333 |  |  | 0 | 467.8333
Total For Account EACH |  | EACH | 12 | 1069.25 | 12831 | 0 | 0 | 0 | 1069.25 | 12 | 1069.25 | 12831 | 0 | 0 | 0 | 0 | 1069.25 | 0 | 0 | 0 | 1069.25 | 0 | 0 | 0 | 1069.25 | 0 | 0 | 0 | 1069.25 | 0% | 0% | 12 | 12831
Account: 0104- 8100- M93 BOLT/WELD INVERTER PILE CAPS
| Labor |  |  | 61.9667 | 7436 |  | 34.7212 | 4166.5473 | 27.2454 |  | 34.7212 | 4166.5473 | -3269.4527 |  |  | 0 | 61.9667 |  |  | 0 | 61.9667 |  |  | 0 | 61.9667 |  |  | 0 | 61.9667
| Equipment |  |  | 17.8 | 2136 |  | 0 | 0 | 17.8 |  | 0 | 0 | -2136 |  |  | 0 | 17.8 |  |  | 0 | 17.8 |  |  | 0 | 17.8 |  |  | 0 | 17.8
Total For Account EACH |  | EACH | 120 | 79.7667 | 9572 | 120 | 34.7212 | 4166.5473 | 45.0454 | 120 | 34.7212 | 4166.5473 | -5405.4527 | 0 | 0 | 0 | 79.7667 | 0 | 0 | 0 | 79.7667 | 0 | 0 | 0 | 79.7667 | 0 | 0 | 0 | 79.7667 | 100% | 43.53% | -1.4211e-14 | 5405.4527
Account: 0105- 2300- M30 UNLOAD PV RACK
| Labor |  |  | 130.3667 | 7822 |  | 180.8252 | 10849.5109 | -50.4585 |  | 180.8252 | 10849.5109 | 3027.5109 |  |  | 656.0443 | 130.3667 |  |  | 588.2238 | 130.3667 |  |  | 568.861 | 130.3667 |  |  | 0 | 130.3667
| Equipment |  |  | 24.5 | 1470 |  | 38.4 | 2304 | -13.9 |  | 38.4 | 2304 | 834 |  |  | 0 | 24.5 |  |  | 0 | 24.5 |  |  | -1254 | 24.5 |  |  | 0 | 24.5
Total For Account LOAD |  | LOAD | 60 | 154.8667 | 9292 | 60 | 219.2252 | 13153.5109 | -64.3585 | 60 | 219.2252 | 13153.5109 | 3861.5109 | 0 | 0 | 656.0443 | 154.8667 | 0 | 0 | 588.2238 | 154.8667 | 0 | 0 | -685.139 | 154.8667 | 0 | 0 | 0 | 154.8667 | 100% | 141.6% | 0 | -3861.5109
Account: 0105- 2300- M31 STAGE & PREP PV RACK
| Labor |  |  | 46.2878 | 45362 |  | 52.632 | 47789.8783 | -6.3443 |  | 52.632 | 51579.3841 | 6217.3841 |  |  | 0 | 46.2878 |  | 186.3856 | 1304.6994 | -140.0979 |  |  | 16.5 | 46.2878 |  |  | 0 | 46.2878
| Equipment |  |  | 6.7806 | 6645 |  | 10.3062 | 9358 | -3.5256 |  | 10.3062 | 10100.0441 | 3455.0441 |  |  | 0 | 6.7806 |  | 0 | 0 | 6.7806 |  |  | -814 | 6.7806 |  |  | 0 | 6.7806
Total For Account EACH |  | EACH | 980 | 53.0684 | 52007 | 908 | 62.9382 | 57147.8783 | -9.8698 | 980 | 62.9382 | 61679.4282 | 9672.4282 | 0 | 0 | 0 | 53.0684 | 7 | 186.3856 | 1304.6994 | -133.3173 | 0 | 0 | -797.5 | 53.0684 | 0 | 0 | 0 | 53.0684 | 92.65% | 109.9% | 72 | -5140.8783
Account: 0105- 2300- M34 ASSEMBLE & SET TORQUE TUBES
| Labor |  |  | 8.9931 | 85884 |  | 19.9504 | 190526.35 | -10.9573 |  | 19.9504 | 190526.35 | 104642.35 |  | 16.3322 | 21182.9217 | -7.3392 |  | 16.9967 | 18985.2726 | -8.0036 |  | -65.2248 | -1369.72 | 74.2179 |  |  | 0 | 8.9931
| Equipment |  |  | 1.9145 | 18283 |  | 1.8905 | 18054 | 0.023979 |  | 1.8905 | 18054 | -229 |  | 2.091 | 2712 | -0.17653 |  | 2.2399 | 2502 | -0.32548 |  | -38.0952 | -800 | 40.0097 |  |  | 0 | 1.9145
Total For Account EACH |  | EACH | 9550 | 10.9075 | 104167 | 9550 | 21.8409 | 208580.35 | -10.9333 | 9550 | 21.8409 | 208580.35 | 104413.35 | 1297 | 18.4232 | 23894.9217 | -7.5157 | 1117 | 19.2366 | 21487.2726 | -8.3291 | 21 | -103.32 | -2169.72 | 114.2275 | 0 | 0 | 0 | 10.9075 | 100% | 200.2% | 0 | -104413.35
Account: 0105- 2300- M36 TORQUE & ALIGN
| Labor |  |  | 6.9651 | 66517 |  | 14.1813 | 133545.6008 | -7.2162 |  | 14.1813 | 135431.7179 | 68914.7179 |  | 95.7255 | 19336.5575 | -88.7604 |  | 6.8413 | 25114.2697 | 0.12387 |  | 520.4183 | 11449.2016 | -513.4531 |  |  | 0 | 6.9651
Total For Account EACH |  | EACH | 9550 | 6.9651 | 66517 | 9417 | 14.1813 | 133545.6008 | -7.2162 | 9550 | 14.1813 | 135431.7179 | 68914.7179 | 202 | 95.7255 | 19336.5575 | -88.7604 | 3671 | 6.8413 | 25114.2697 | 0.12387 | 22 | 520.4183 | 11449.2016 | -513.4531 | 0 | 0 | 0 | 6.9651 | 98.61% | 200.8% | 133 | -67028.6007
Account: 0109- 5170- M37 INSTALL MOTOR
| Labor |  |  | 98.0256 | 3823 |  | 26.0959 | 495.8226 | 71.9297 |  | 26.0959 | 1017.7411 | -2805.2589 |  | 27.5457 | 495.8226 | 70.4799 |  |  | 0 | 98.0256 |  | 0 | 0 | 98.0256 |  |  | 0 | 98.0256
Total For Account EACH |  | EACH | 39 | 98.0256 | 3823 | 19 | 26.0959 | 495.8226 | 71.9297 | 39 | 26.0959 | 1017.7411 | -2805.2589 | 18 | 27.5457 | 495.8226 | 70.4799 | 0 | 0 | 0 | 98.0256 | 0 | 0 | 0 | 98.0256 | 0 | 0 | 0 | 98.0256 | 48.72% | 12.97% | 20 | 3327.1774
Account: 0109- 5170- M38 INSTALL DRIVELINE
| Labor |  |  | 344.6154 | 4480 |  |  | 0 | 344.6154 |  | 344.6154 | 4480 | 0 |  |  | 0 | 344.6154 |  |  | 0 | 344.6154 |  |  | 0 | 344.6154 |  |  | 0 | 344.6154
Total For Account EACH |  | EACH | 13 | 344.6154 | 4480 | 0 | 0 | 0 | 344.6154 | 13 | 344.6154 | 4480 | 0 | 0 | 0 | 0 | 344.6154 | 0 | 0 | 0 | 344.6154 | 0 | 0 | 0 | 344.6154 | 0 | 0 | 0 | 344.6154 | 0% | 0% | 13 | 4480
Account: 0109- 5210- M80 UNLOAD PANEL
| Labor |  |  | 0.28366 | 25658 |  | 0.19465 | 17606.5281 | 0.089012 |  | 0.19465 | 17606.5281 | -8051.472 |  |  | 574.2152 | 0.28366 |  | 0 | 0 | 0.28366 |  |  | 0 | 0.28366 |  |  | 0 | 0.28366
| Equipment |  |  | 0.05458 | 4937 |  | 0.053663 | 4854 | 0.00091759 |  | 0.053663 | 4854 | -83 |  |  | 352 | 0.05458 |  | 0 | 0 | 0.05458 |  |  | -1122 | 0.05458 |  |  | 0 | 0.05458
Total For Account EACH |  | EACH | 90454 | 0.33824 | 30595 | 90454 | 0.24831 | 22460.5281 | 0.089929 | 90454 | 0.24831 | 22460.5281 | -8134.472 | 0 | 0 | 926.2152 | 0.33824 | 0 | 0 | 0 | 0.33824 | 0 | 0 | -1122 | 0.33824 | 0 | 0 | 0 | 0.33824 | 100% | 73.41% | 0 | 8134.472
Account: 0109- 5210- M81 STAGE PV PANEL
| Labor |  |  | 0.36615 | 33120 |  | 0.17112 | 15762.2688 | 0.19503 |  | 0.17112 | 15762.2688 | -17357.7312 |  | 0.15352 | 1213.4222 | 0.21263 |  | 0.058526 | 2678.144 | 0.30763 |  | 0.79361 | 1314.226 | -0.42746 |  |  | 0 | 0.36615
| Equipment |  |  | 0.11237 | 10164 |  | 0.033612 | 3096 | 0.078755 |  | 0.033612 | 3096 | -7068 |  | 0.052632 | 416 | 0.059735 |  | 0.042308 | 1936 | 0.070059 |  | 0.060386 | 100 | 0.05198 |  |  | 0 | 0.11237
Total For Account EACH |  | EACH | 90454 | 0.47852 | 43284 | 92110 | 0.20474 | 18858.2688 | 0.27378 | 92110 | 0.20474 | 18858.2688 | -24425.7312 | 7904 | 0.20615 | 1629.4222 | 0.27237 | 45760 | 0.10083 | 4614.144 | 0.37769 | 1656 | 0.854 | 1414.226 | -0.37548 | 0 | 0 | 0 | 0.47852 | 101.8% | 43.57% | -1656 | 24425.7312
Account: 0109- 5210- M82 INSTALL PV PANEL
| Labor |  |  | 2.3452 | 212134 |  | 5.6895 | 333567.839 | -3.3443 |  | 5.6895 | 514635.1687 | 302501.1687 |  | 6.0613 | 36719.2245 | -3.7161 |  | 9.3307 | 48360.8049 | -6.9854 |  | 8.9617 | 61620.5315 | -6.6165 |  | 2.9462 | 34626.3631 | -0.60096
| Equipment |  |  | 0.059434 | 5376 |  | 0.16586 | 9724 | -0.10642 |  | 0.16586 | 15002.3827 | 9626.3827 |  | 0.52427 | 3176 | -0.46483 |  | 0.38626 | 2002 | -0.32683 |  | 0.20448 | 1406 | -0.14505 |  | 0.086786 | 1020 | -0.027353
Total For Account EACH |  | EACH | 90454 | 2.4046 | 217510 | 58629 | 5.8553 | 343291.839 | -3.4507 | 90454 | 5.8553 | 529637.5514 | 312127.5514 | 6058 | 6.5855 | 39895.2245 | -4.1809 | 5183 | 9.7169 | 50362.8049 | -7.3123 | 6876 | 9.1662 | 63026.5315 | -6.7615 | 11753 | 3.033 | 35646.3631 | -0.62831 | 64.82% | 157.8% | 31825 | -125781.839
Account: 0109- 5220- M92 SET INVERTER
| Labor |  |  | 796 | 9552 |  | 980.6439 | 11767.727 | -184.6439 |  | 980.6439 | 11767.727 | 2215.727 |  |  | 0 | 796 |  |  | 0 | 796 |  |  | 0 | 796 |  |  | 0 | 796
Total For Account EACH |  | EACH | 12 | 796 | 9552 | 12 | 980.6439 | 11767.727 | -184.6439 | 12 | 980.6439 | 11767.727 | 2215.727 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 796 | 100% | 123.2% | 0 | -2215.727
Account: 0196- 2003- 000 FORCE CODE #3 - MECHANICAL REMEDIATION
| Labor |  |  | 0 | 0 |  |  | 72897.7907 | 0 |  | 0 | 72897.7907 | 72897.7907 |  |  | 0 | 0 |  |  | 26037.636 | 0 |  |  | 41532.2563 | 0 |  |  | 5327.8984 | 0
| Equipment |  |  | 0 | 0 |  |  | 315 | 0 |  | 0 | 315 | 315 |  |  | 0 | 0 |  |  | 315 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total For Account ? |  | ? | 0 | 0 | 0 | 0 | 0 | 73212.7907 | 0 | 0 | 0 | 73212.7907 | 73212.7907 | 0 | 0 | 0 | 0 | 0 | 0 | 26352.636 | 0 | 0 | 0 | 41532.2563 | 0 | 0 | 0 | 5327.8984 | 0 | 0% | 0% | 0 | -73212.7907
Account: 0196- 2004- 000 FORCE CODE #4 - MECHANICAL AVOIDANCE AREA WORK
| Labor |  |  | 0 | 0 |  | 26.6912 | 7473.5345 | -26.6912 |  | 0 | 7473.5345 | 7473.5345 |  |  | 0 | 0 |  |  | 0 | 0 |  | 25.3867 | 5153.5001 | -25.3867 |  | 30.1303 | 2320.0343 | -30.1303
| Equipment |  |  | 0 | 0 |  | 8.9429 | 2504 | -8.9429 |  | 0 | 2504 | 2504 |  |  | 0 | 0 |  |  | 0 | 0 |  | 8.5123 | 1728 | -8.5123 |  | 10.0779 | 776 | -10.0779
Total For Account ? |  | ? | 0 | 0 | 0 | 280 | 35.6341 | 9977.5344 | -35.6341 | 0 | 0 | 9977.5344 | 9977.5344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 33.899 | 6881.5001 | -33.899 | 77 | 40.2082 | 3096.0343 | -40.2082 | 0% | 0% | -280 | -9977.5344
Account: UNPAID LUNCH UNPAID LUNCH
| Labor |  |  | 0 | 0 |  | 27.908 | 30112.7785 | -27.908 |  | 0 | 30112.7785 | 30112.7785 |  | 27.0283 | 2783.917 | -27.0283 |  | 27.4592 | 5217.2432 | -27.4592 |  | 27.2206 | 4913.3243 | -27.2206 |  | 27.3162 | 1584.3384 | -27.3162
Total For Account - |  | HR | 0 | 0 | 0 | 1079 | 27.908 | 30112.7785 | -27.908 | 0 | 0 | 30112.7785 | 30112.7785 | 103 | 27.0283 | 2783.917 | -27.0283 | 190 | 27.4592 | 5217.2432 | -27.4592 | 180.5 | 27.2206 | 4913.3243 | -27.2206 | 58 | 27.3162 | 1584.3384 | -27.3162 | 0% | 0% | -1079 | -30112.7785
Total For Job 55310.M |  |  |  |  | 832528 |  |  | 1240900.9144 |  |  |  | 1451497.2123 | 618969.2123 |  |  | 93366.99 |  |  |  | 138590.0089 |  |  |  | 126311.7104 |  |  |  | 45779.2758
† Original Contract does not include change orders